## 1. Execution Roadmap
Task ID | Stage | Order | Component | Feature Name | Purpose & Why It Is Needed | Detailed Technical Implementation | Target Domains Unlocked | Est. Effort | Status
CORE-01 | Core / Basic | Step 1 | Type Checker & Codegen | Result<T, E> & Option<T> Types | Prevent runtime panics on I/O, file, network, and database operations. Fully replaces process crashes with safe error propagation (? operator). | Result/Option types in semantic checker; unwrap, unwrap_or, unwrap_err, is_ok, is_err, is_some, is_none; safe IO intrinsics (read_file_result, write_file_result, etc.); safe collection indexing (list_get_option, map_get_option); postfix '?' try operator hoisting with early return in JVM and native backends. | Web/Enterprise, Systems, Tooling, Self-Hosting | Completed | Completed
CORE-02 | Core / Basic | Step 2 | Frontend & Type Checker | Enums (ADTs) & Pattern Matching | Essential for representing AST nodes, tokens, and domain states cleanly without hacky integer flags or unsafe casting. | Syntax 'enum Name { Variant(Type), ... }'; pattern matching 'match expr { Variant(val) => ... }'; lower to Typed IR; codegen tagged union with tag + payload in Cranelift native; Java sealed classes/records in JVM. | Compiler Self-Hosting, Web, Security | Completed | Completed
CORE-03 | Core / Basic | Step 3 | Frontend, JVM & Native | Closures & First-Class Functions | Enable passing functions as arguments. Strictly required for web request routing, callbacks, event handling, list map/filter, and concurrency task dispatch. | Syntax 'let f = ¦x: int¦ -> int { x + 1 };'; function types 'func(int) -> int'; closure environment capture struct; JVM java.util.function emission; Native function pointer + env pointer. | Web Framework (Routing/Middleware), GUI, Games | Completed | Completed
CORE-04 | Core / Basic | Step 4 | Type Checker & Native Codegen | Generics (Parametric Polymorphism) | Provide type-safe generic data structures (List<T>, Map<K, V>). Eliminates Object boxing on JVM and unlocks strings/structs inside native lists. | Syntax 'class Container<T> { val: T }' and generic functions 'func id<T>(x: T) -> T'; Native monomorphization (specialize code per type); JVM type parameters with erasure. | All Domains, Core Stdlib, Self-Hosting | Completed | Completed
CORE-05 | Core / Basic | Step 5 | Frontend & Semantic Checker | Traits / Interfaces & Dynamic Dispatch | Define behavioral contracts without inheritance. Foundation of Spring-Boot-style Dependency Injection (IoC) and pluggable modular architecture. | Syntax 'trait Greeter { func greet() -> string; }' and 'impl Greeter for User { ... }'; JVM interface generation; Native vtable pointer in class headers. | Enterprise Architecture, Games, Plugins | Completed | Completed
MED-01 | Medium | Step 6 | Native Codegen (Cranelift) | Foreign Function Interface (C-ABI FFI) | The Universal Key: Call ANY existing C/C++ library directly. Instantly unlocks Desktop (GTK/Qt/Win32), Games (Raylib/SDL3/Vulkan), AI/ML (BLAS/CUDA/PyTorch), and Security (libpcap/OpenSSL) without rewriting them. | Syntax 'extern "C" func printf(fmt: string) -> int;'; Cranelift SystemV / Win64 calling convention integration; link external shared/static libraries via 'roze build --link <lib>'. | Desktop GUI, Games, AI/ML, Security/Hacking, Systems | Completed | Completed
MED-02 | Medium | Step 7 | Native Runtime & Codegen | Thread-Safe Atomic ARC | Make memory management thread-safe. Prevents race conditions and use-after-free corruption when data is accessed across concurrent threads. | Upgrade ARC retain and release helper functions in Cranelift from plain increment/decrement to atomic operations (lock xadd / Cranelift atomic load/store/rmw). | Web Servers, Multi-threaded Games, Systems | Completed | Completed
MED-03 | Medium | Step 8 | Runtime & Standard Library | Native Concurrency: Threads & Channels | Allow spawning background worker threads and passing messages safely between threads without data races. | 'thread_spawn(func)' backed by OS threads (pthread / Windows CreateThread) or JVM virtual threads; channel primitives ('channel_new()', 'send()', 'recv()') with ring buffer and lock. | Enterprise Servers, Game Engines, Systems | Completed | Completed
MED-04 | Medium | Step 9 | Standard Library (Web & Net) | Concurrent Async HTTP Server & Router | Replace single-threaded synchronous server with a high-performance HTTP server capable of serving thousands of simultaneous requests. | Thread pool worker dispatch loop; URL route matcher ('/api/users/:id'); JSON body auto-deserialization; middleware pipeline for auth/logging. | Enterprise Web Backends, Cloud Services | Completed | Completed
MED-05 | Medium | Step 10 | Frontend & Native Backend | Unsafe Raw Pointers & Direct Memory | Low-level direct memory access for security research, packet inspection, hardware I/O, binary reverse-engineering, and high-speed game buffers. | 'unsafe { ... }' block syntax; raw pointer types '*raw u8', '*raw int'; pointer read/write intrinsics; direct memory allocation without ARC header overhead. | Security/Hacking, OS Development, Game Engines | Completed | Completed
MED-06 | Medium | Step 11 | Tooling (roze-pkg) | Package Registry & Dependency Resolver | Allow developers to install, share, and manage third-party libraries seamlessly from a central registry or Git repos. | Implement Git-based dependency fetching, semantic version resolution (semver), lockfile generation ('roze.lock'), and binary package caching. | Developer Experience, Ecosystem Growth | Completed | Completed
ADV-01 | Advanced | Step 12 | Native Codegen & Linker | Freestanding / no_std Kernel Target | Compile code that runs directly on bare metal CPU with zero OS, zero glibc, and zero mandatory runtime underneath. | '--target freestanding' compiler flag; custom '_start' entry point; disable libc malloc/printf; raw VGA buffer text driver; linker script integration. | Operating System Kernel, Embedded Firmware | 1 - 2 Weeks | Ready to Start
ADV-02 | Advanced | Step 13 | Systems & OS Demo | Bootable x86_64 OS Kernel Demo | Provide indisputable proof that Roze can build an operating system from scratch. | Write a minimal 64-bit multiboot2 kernel in Roze; boot via GRUB/QEMU; print hardware info and manage basic physical memory frames. | Operating System Proof-of-Concept | 1 - 2 Weeks | Planned
ADV-03 | Advanced | Step 14 | Web Framework Project | Spring-Boot-Style Framework ('RozeBoot') | Enable building large-scale enterprise services with declarative controllers, middleware, connection pooling, and ORM query builders. | Build 'RozeBoot' framework on top of Roze: REST controller annotations/routing, HikariCP JDBC connection pooling, JWT security, SQL query builder. | Enterprise Cloud Applications | 2 - 3 Weeks | Planned
ADV-04 | Advanced | Step 15 | Game Engine Demo | 2D/3D Game Demo via FFI (Raylib / SDL3) | Demonstrate game platform capabilities with 60 FPS real-time rendering, audio, and physics. | Bind Raylib / SDL3 via Roze C-FFI; build a working game loop with sprite rendering, keyboard/mouse input, particle effects, and sound playback. | Game Platform Proof-of-Concept | 1 Week | Planned
ADV-05 | Advanced | Step 16 | AI / ML Wrapper Project | AI & ML Inference Wrapper (ONNX / GGML) | Run local AI models (Llama, BERT, Vision models) directly from Roze apps. | Bind ONNX Runtime C API or GGML via FFI; load model weights; pass input tensors; run inference and parse prediction outputs. | AI / ML Applications, Data Science | 1 - 2 Weeks | Planned
ADV-06 | Advanced | Step 17 | Compiler Re-Architecture | Self-Hosting Compiler (Roze-in-Roze) | Rewrite the Roze compiler in Roze itself, removing all dependency on Rust and proving the language's ultimate maturity. | Implement Roze lexer, parser, type checker, and Cranelift/C code generation in pure Roze; compile the Roze compiler using itself. | Self-Hosting, Language Independence | 3 - 4 Weeks | Planned
ADV-07 | Advanced | Step 18 | Release Engineering | Official v1.0.0 Release, Docs & Ecosystem | Complete production release with semantic versioning guarantees, online documentation, VS Code marketplace extension, and installer packages. | Finalize language grammar specification; publish VS Code extension; release Debian/RPM/Homebrew/Windows MSI packages; launch Roze package registry. | Official v1.0.0 Public Launch | 2 Weeks | Planned

## 2. Domain Capability Matrix
Target Domain | Vision & Target Applications | Current Roze State | Gaps to Close | Enabling Tasks (From Roadmap) | Industry Benchmark | Current Readiness
Enterprise Web & Microservices | Spring-Boot-level servers, REST/gRPC APIs, Cloud services, banking & enterprise backends | JVM HTTP accept loop, JSON, JDBC SQL, Result<T,E> & Option<T> Safe I/O | Multi-threaded concurrency, closures/routing, generics, connection pooling | CORE-01 (Done), CORE-02 (Done), CORE-03 (Done), CORE-04 (Done), CORE-05 (Done), MED-02 (Done), MED-04 (Done), ADV-03 | Java (Spring Boot), Go (Gin/Fiber), C# (.NET) | 75% - Concurrent Server & Router Ready
Operating Systems & Kernels | Monolithic/microkernel OS, custom bootloaders, hardware drivers, embedded firmware | Cranelift native backend emits standalone ELF/PE binaries with libc ARC | Bare-metal freestanding mode (no glibc, no malloc), raw unsafe pointers, inline assembly, linker scripts | MED-05 (Done), ADV-01, ADV-02 | C, Rust (no_std), Zig | 25% - Unsafe Pointers Ready
Security & Penetration Testing | Custom network sniffers, exploit payloads, binary reverse-engineering tools, memory analyzers | Native standalone executables, TCP sockets, float/math, safe Result error handling | Raw byte buffers, unsafe memory pointers, FFI bindings to libpcap, OpenSSL, and raw packet sockets | MED-01 (Done), MED-05 (Done) | Python (Scapy), Go, C, Rust | 60% - Raw Memory & FFI Ready
Games & Interactive Platforms | 2D & 3D game engines, indie games, physics simulation, cross-platform game runtime | ARC-managed classes and lists, IEEE-754 f64 math, fast native execution | FFI to Raylib/SDL3/Vulkan, atomic multi-threaded rendering/audio threads, generics for ECS engines | CORE-04 (Done), MED-01 (Done), MED-02 (Done), ADV-04 | C++, C# (Unity), Rust (Bevy), C | 50% - Atomic ARC & FFI Ready
AI / Machine Learning | Local LLM inference (Llama), computer vision, neural net inference, data pipelines | Fast f64 double precision numbers, basic arrays/lists, Result safety | C-FFI to bind ONNX Runtime, libtorch, or GGML tensor libraries | CORE-04 (Done), MED-01 (Done), ADV-05 | Python (PyTorch wrapper), C++ | 45% - FFI Enabled
Desktop GUI Applications | Cross-platform desktop tools, productivity software, native UI apps | Fast standalone executables on Windows, Linux, and macOS | FFI to native UI toolkits (GTK4, Qt, Win32, Cocoa), closure event handlers | CORE-03 (Done), MED-01 (Done) | C# (WPF), Rust (Tauri), C++ (Qt) | 50% - Closures & FFI Completed
Self-Hosting Compiler | The Roze compiler written entirely in Roze with zero external dependencies | Clean AST/IR, Result/Option safe error handling with '?' try operator | Generics, Enums/Pattern Matching, file I/O on native backend | CORE-01 (Done), CORE-02 (Done), CORE-03 (Done), CORE-04 (Done), CORE-05 (Done), ADV-06 | Rust (rustc), Go (gc), Swift | 65% - Traits & Generics Completed

## 3. Phases & Milestones
Phase Name | Strategic Focus | Key Deliverables | Prerequisites | Target Milestone | Status / Success Criteria
Phase 1 | Core Language Maturity & Safety | Result/Option error types (Done), Enums with Pattern Matching (Done), Closures/Lambdas (Done), Generics (Done), Traits/Interfaces (Done) | Existing 1.99.1 Compiler | v0.2.0-alpha | COMPLETED (Phase 1 100% Complete)
Phase 2 | Universal Interop & Concurrency | C-ABI FFI (extern 'C'), Thread-safe Atomic ARC, Native OS Threads & Channels, Concurrent Async HTTP Server, Package Registry & Dependency Resolver (roze-pkg) | Phase 1 Core Types | v0.5.0-beta | COMPLETED (Phase 2 100% Complete)
Phase 3 | Low-Level Systems & Freestanding | Unsafe raw pointers, Direct memory operations, --target freestanding (no_std), Bootable OS x86_64 kernel demo | Phase 2 C-ABI & ARC | v0.7.0-systems | Ready to Start
Phase 4 | Multi-Domain Proof Points | 'RozeBoot' Enterprise Framework, 60 FPS 2D Game demo via Raylib, Local AI inference via GGML/ONNX | Phases 1, 2, and 3 | v0.9.0-rc1 | Planned
Phase 5 | Self-Hosting & Official v1.0.0 | Roze compiler rewritten in Roze; Package Registry; VS Code extension on marketplace; v1.0.0 Stable Release | Phase 1-4 Complete | v1.0.0 Stable | Planned