## 1. 6-Month Master Plan
Task ID | Month | Sprint & Weeks | Domain / Epic | Feature & Capability | Detailed Technical Implementation | Java 25 & Rust 1.99.1 Parity Deliverables | Target Domains Unlocked | Est. Days | Priority | Status
M1-T01 | Month 1 | Sprint 1 (W01-W02) | Core Type System | Advanced Generics & Trait Bounds | Implement monomorphization engine and trait bounds syntax (<T: Display + Clone>). Add associated types ('trait Iterator { type Item; }') and higher-kinded polymorphism ergonomics. | Matches Rust trait bounds and Java bounded type parameters (<T extends Comparable<T>>); enables universal generic collections. | All Domains, Core Stdlib, Compiler | 7 Days | Critical | Completed
M1-T02 | Month 1 | Sprint 1 (W01-W02) | Pattern Matching | Deep Destructuring & Match Guards | Exhaustive pattern matching compiler for nested enums, struct fields, tuples, slice patterns ([head, ..tail]), range patterns (1..=10), and 'if' match guards. | Parity with Rust 1.99 pattern matching and Java 25 Pattern Matching for switch and Record Patterns. | Compiler, Web Framework, Security | 7 Days | High | Completed
M1-T03 | Month 1 | Sprint 1 (W01-W02) | Metaprogramming | Compile-Time Function Execution (comptime) | Add 'comptime' expression evaluator in compiler semantic pass. Evaluate constant math, generate lookup tables, and compute type layouts during compilation. | Matches Zig comptime and Rust const fn capabilities; eliminates runtime overhead for static structures. | Games, OS Kernels, AI/ML Tensors | 6 Days | High | Completed
M1-T04 | Month 1 | Sprint 2 (W03-W04) | Modern Concurrency | M:N Green Threads (Virtual Threads) | Implement cooperative user-space green thread scheduler with work-stealing threadpool across OS worker threads. Zero allocation fiber context switching. | Parity with Java 25 Project Loom Virtual Threads and Go goroutines. Supports 1,000,000 simultaneous concurrent tasks. | Enterprise Web, Game Servers, Tools | 8 Days | Critical | Planned
M1-T05 | Month 1 | Sprint 2 (W03-W04) | Async Runtime | Async / Await State-Machine Engine | Lower 'async func' and 'await' expressions to zero-allocation state machine generator structs. Native Future<T> polling contract with reactor integration. | Full parity with Rust async/await and modern Java CompletableFuture / Structured Concurrency. | Web Microservices, Network I/O | 8 Days | Critical | Planned
M1-T06 | Month 1 | Sprint 2 (W03-W04) | Synchronization | Lock-Free Primitives & Channels | Atomic types (AtomicBool, AtomicI64, AtomicPtr, AtomicUsize). Implement high-throughput MPMC bounded and unbounded ring-buffer channels, Mutex, and RwLock. | Matches Rust std::sync and Java java.util.concurrent.atomic / locks. | Enterprise, Game Engines, Systems | 6 Days | High | Planned
M1-T07 | Month 1 | Sprint 2 (W03-W04) | Structured Concurrency | Nursery, Task Groups & Cancelation | Nursery structured concurrency scope: parent task automatically awaits all spawned child tasks. Unified cancelation tokens and timeout triggers. | Parity with Java 25 JEP 453 Structured Concurrency and Rust nursery runtimes. | Cloud Microservices, Distributed Systems | 5 Days | Medium | Planned
M1-T08 | Month 1 | Sprint 2 (W03-W04) | Milestone Gate M1 | Month 1 Integration & Concurrency Benchmark | Verify 100,000 concurrent green thread ping-pong message test over MPMC channels. Monomorphized generic data structures stress test suite. | 100% test pass on all concurrency and advanced type fixtures. | All Domains | 3 Days | Critical | Milestone Gate
M2-T01 | Month 2 | Sprint 3 (W05-W06) | Core Types | Full Fixed-Width Numeric Suite | Introduce complete primitive numeric types: i8, u8, i16, u16, i32, u32, i64, u64, i128, u128, f32, f64, isize, usize, and char with wrapping/saturating arithmetic. | Complete parity with Rust numeric primitives and Java 25 wrapper classes with unsigned support. | OS, Systems, Security, AI/ML, Games | 5 Days | Critical | Planned
M2-T02 | Month 2 | Sprint 3 (W05-W06) | Hardware Acceleration | SIMD Vector Intrinsics Engine | Hardware SIMD types: Vec4f, Vec8f, Vec4i, Vec16u8 with AVX-512, AVX2, and ARM NEON code generation for 8x-16x vector processing acceleration. | Matches Java 25 Vector API (incubator) and Rust core::simd. | AI/ML Tensors, Game Physics, Video/Audio | 7 Days | High | Planned
M2-T03 | Month 2 | Sprint 3 (W05-W06) | Standard Collections | Advanced High-Performance Collections | Implement VecDeque<T>, BTreeMap<K, V>, BTreeSet<T>, BinaryHeap<T> (priority queue), IndexMap<K, V>, RingBuffer<T>, and BitSet with amortized O(1) ops. | Parity with Rust std::collections and Java 25 java.util collections hierarchy. | All Domains, Databases, Frameworks | 8 Days | High | Planned
M2-T04 | Month 2 | Sprint 3 (W05-W06) | Memory Architecture | Pluggable Allocator API & Smart Pointers | Arena Allocator, Bump Allocator, Fixed-Size Block Pool Allocator, Box<T>, Arc<T>, and Weak<T> with cyclic reference detection and cache alignment. | Parity with Rust Allocator API and modern C++ polymorphic allocators (PMR). | OS Development, High-Frequency Trading, Games | 6 Days | High | Planned
M2-T05 | Month 2 | Sprint 4 (W07-W08) | Freestanding Systems | Bare-Metal Kernel Target (--target freestanding) | Zero-libc, zero-heap bare metal target. Custom linker script integration, freestanding runtime entry (_start), and disabling float registers for ISR. | Parity with Rust #![no_std] and Zig freestanding target; produces standalone bootable binaries. | Operating Systems, Microcontrollers | 7 Days | Critical | Planned
M2-T06 | Month 2 | Sprint 4 (W07-W08) | Kernel Memory | 4-Level Paging & Virtual Memory Manager | PML4 -> PDPT -> PD -> PT page table manipulator. 4KB and 2MB huge page mapping, physical frame allocator (Bitmap + Buddy allocator), and TLB invalidation. | Full OS memory management stack written entirely in Roze. | Operating System Development | 8 Days | Critical | Planned
M2-T07 | Month 2 | Sprint 4 (W07-W08) | Kernel Core | Hardware Interrupts (GDT, IDT, APIC) | Global Descriptor Table, Interrupt Descriptor Table with 256 vector stubs, Exception handlers (Page Fault #PF, GPF #GP), and Local APIC / 8259 PIC driver. | Production kernel interrupt handling with zero host OS dependencies. | Operating System Development | 7 Days | High | Planned
M2-T08 | Month 2 | Sprint 4 (W07-W08) | Hardware Drivers | UART, Keyboard, Timer & GOP Framebuffer | 16550 UART serial driver, PS/2 keyboard/mouse interrupt driver, PIT/HPET high-res timer, and UEFI GOP linear framebuffer graphics. | Hardware I/O driver library in pure Roze. | Operating Systems, Embedded Firmware | 6 Days | High | Planned
M2-T09 | Month 2 | Sprint 4 (W07-W08) | Inline Assembly | Native asm! Macro & Register Constraints | Inline assembly syntax: asm! { 'out dx, al', in('dx') port, in('al') val, options(nomem, nostack) } with x86_64 and ARM64 register constraints. | Parity with Rust core::arch::asm! and GCC inline assembly. | Operating Systems, Security Exploits | 6 Days | Critical | Planned
M2-T10 | Month 2 | Sprint 4 (W07-W08) | Milestone Gate M2 | Month 2 Bootable OS Kernel Verification | Boot RozeOS Kernel v2 in QEMU via GRUB/Multiboot2: initialize paging, heap allocator, IDT, print to VGA/GOP screen, and execute interactive shell. | QEMU x86_64 automated CI boot test with zero kernel panics. | Operating Systems & Freestanding | 3 Days | Critical | Milestone Gate
M3-T01 | Month 3 | Sprint 5 (W09-W10) | Raw Networking | Raw Sockets & Promiscuous Sniffing | AF_PACKET / BPF raw socket engine in roze::net::raw. Binds directly to network interfaces in promiscuous mode with zero-copy packet ring buffer. | Parity with Python Scapy and Go gopacket; native raw socket capture without external dependencies. | Cybersecurity, Hacking, Pen-Testing | 6 Days | High | Planned
M3-T02 | Month 3 | Sprint 5 (W09-W10) | Packet Crafting | Protocol Builder & Packet Dissector | Packet crafting and dissection engine for Ethernet, ARP, IPv4, IPv6, ICMP, TCP (custom flags/SYN/ACK), UDP, DNS, and DHCP. Automated checksum calculation. | Full packet injection and inspection framework. | Cybersecurity, Network Engineering | 7 Days | High | Planned
M3-T03 | Month 3 | Sprint 5 (W09-W10) | Security Scanning | Ultra-Fast SYN Port & Banner Scanner | Asynchronous SYN stealth scanner utilizing green threads. Scans 100,000+ ports per second, captures service banners, and identifies OS fingerprints. | Matches Nmap SYN scan performance in pure Roze. | Cybersecurity, Reconnaissance Tools | 6 Days | High | Planned
M3-T04 | Month 3 | Sprint 5 (W09-W10) | Standard Cryptography | Full Crypto Suite & Pure TLS 1.3 | roze::crypto module: AES-128/256-GCM, ChaCha20-Poly1305, SHA-256, SHA-512, SHA-3/Keccak, HMAC, Argon2id, Ed25519, Curve25519 (X25519), RSA-4096, and TLS 1.3 handshake. | Matches Java Cryptography Architecture (JCA) and Rust ring/rustls; zero OpenSSL dependency. | Security, Web Backends, Authentication | 9 Days | Critical | Planned
M3-T05 | Month 3 | Sprint 5 (W09-W10) | Binary Analysis | ELF / PE / Mach-O Disassembler Engine | Binary parsing and disassembly engine: parse headers, sections, export/import tables, demangle symbols, and disassemble x86_64 and ARM64 machine opcodes. | Matches capabilities of radare2 and Capstone disassembler. | Reverse Engineering, Malware Analysis | 8 Days | High | Planned
M3-T06 | Month 3 | Sprint 5 (W09-W10) | Exploit Research | Memory Forensics & Shellcode Harness | Cross-platform process memory inspection (/proc/<pid>/mem & VirtualAllocEx), ROP gadget scanner, memory pattern searcher, and shellcode execution sandbox. | Standard penetration testing exploit harness in Roze. | Cybersecurity, Vulnerability Research | 7 Days | Medium | Planned
M3-T07 | Month 3 | Sprint 6 (W11-W12) | Enterprise Web Core | Asynchronous HTTP/1.1, HTTP/2 & HTTP/3 | Multi-core non-blocking event-driven web server powered by epoll/kqueue/IOCP. Zero-copy header parsing, HTTP/2 multiplexed streams, and HTTP/3 QUIC support. | Performance beats Node.js/Go; on par with Rust Actix-web and Java 25 Netty. | Enterprise Web, Cloud Microservices | 8 Days | Critical | Planned
M3-T08 | Month 3 | Sprint 6 (W11-W12) | Enterprise Framework | RozeBoot 2.0 Annotations & IoC Container | Declarative annotations: @RestController, @GetMapping, @PostMapping, @PathVariable, @RequestParam, @RequestBody, @Autowired, @Service, @Component, @Valid. IoC container. | 1:1 architectural parity with Spring Boot 3 on Java 25. | Enterprise Cloud Services | 8 Days | Critical | Planned
M3-T09 | Month 3 | Sprint 6 (W11-W12) | Data & ORM | High-Throughput ORM & SQL Query Builder | Native connection pool (HikariCP equivalent), ActiveRecord / Repository entity mapping, type-safe SQL query builder, automatic schema migrations, and transactions. | Matches Spring Data JPA and Rust Diesel/SeaORM. | Enterprise Banking, SaaS Platforms | 7 Days | High | Planned
M3-T10 | Month 3 | Sprint 6 (W11-W12) | Web Security & Cloud | JWT, OAuth2, Metrics & OpenAPI 3.1 | Built-in JWT auth filter, OAuth2 token validation, Argon2id password hashing, Prometheus /metrics endpoint, OpenTelemetry tracing, and auto-generated Swagger UI docs. | Matches Spring Security and Quarkus observability stack. | Enterprise Backends, Microservices | 6 Days | High | Planned
M3-T11 | Month 3 | Sprint 6 (W11-W12) | Milestone Gate M3 | Month 3 Web & Security Integration Gate | Deploy RozeBoot REST microservice serving 100,000 req/sec under load test. Execute penetration testing suite verifying raw packet sniffer, SYN scanner, and crypto. | Sub-millisecond P99 latency under 50,000 concurrent web connections. | Web Enterprise & Cybersecurity | 3 Days | Critical | Milestone Gate
M4-T01 | Month 4 | Sprint 7 (W13-W14) | AI Tensor Engine | N-Dimensional Tensor<T, D> Engine | Multi-dimensional tensor structure supporting arbitrary ranks, strided views, continuous memory, broadcasting, slicing (tensor[0..5, :, 1]), and transposition. | Parity with NumPy ndarray and PyTorch torch.Tensor. | AI/ML, Data Science, Scientific Computing | 8 Days | Critical | Planned
M4-T02 | Month 4 | Sprint 7 (W13-W14) | AI Acceleration | GEMM / BLAS & GPU Compute (CUDA/Metal) | Hardware-accelerated matrix multiplication kernels: AVX-512 FMA vector code generator + direct CUDA PTX / Apple Metal Shading Language GPU kernels. | Matches cuBLAS and Apple Accelerate performance for neural operations. | AI/ML Deep Learning, LLM Inference | 8 Days | Critical | Planned
M4-T03 | Month 4 | Sprint 7 (W13-W14) | Deep Learning | Reverse-Mode Automatic Differentiation (Autograd) | Dynamic computational tape recording forward ops. Automated backward-pass gradient propagation for complex neural networks and loss functions. | Matches PyTorch Autograd and JAX automatic differentiation. | Machine Learning Training & Fine-Tuning | 7 Days | High | Planned
M4-T04 | Month 4 | Sprint 7 (W13-W14) | Neural Network Layers | Comprehensive NN Layer Library (roze::nn) | Linear/Dense, Conv1D, Conv2D, MaxPool, LayerNorm, RMSNorm, Dropout, Multi-Head Attention, RoPE (Rotary Position Embeddings), and SwiGLU activations. | Matches PyTorch torch.nn module ecosystem. | AI/ML Computer Vision & NLP | 7 Days | High | Planned
M4-T05 | Month 4 | Sprint 7 (W13-W14) | Model Formats | GGUF & ONNX Native Model Loaders | Native binary parser for GGUF (Llama, Mistral, Qwen) and ONNX files. Memory-mapped weight loading (mmap) with Q4_K_M, Q8_0, and FP16 dequantization. | Zero C++ dependency loader matching llama.cpp format. | Local AI Inference, Edge AI | 7 Days | Critical | Planned
M4-T06 | Month 4 | Sprint 7 (W13-W14) | LLM Inference | Local LLM Inference Engine & KV-Cache | Complete Transformer decoder pipeline in pure Roze: BPE tokenizer, rotary embeddings, KV-cache, top-p/top-k sampling, and streaming token generation. | Run LLaMA 3 8B locally in Roze with 45+ tokens/sec on Apple Silicon / CUDA. | AI Applications, Local Copilots | 8 Days | Critical | Planned
M4-T07 | Month 4 | Sprint 8 (W15-W16) | Game Math | Complete 2D/3D Game Math Suite | Vec2, Vec3, Vec4, Mat3x3, Mat4x4, Quaternion, Transform, Ray, Plane, AABB, and Frustum with SIMD-accelerated linear algebra operations. | Parity with Rust glam/nalgebra and C++ GLM. | Game Development, Physics Simulation, VFX | 6 Days | High | Planned
M4-T08 | Month 4 | Sprint 8 (W15-W16) | Graphics HAL | Cross-Platform Graphics Hardware Abstraction | Unified rendering backend: Vulkan 1.3, Apple Metal, DirectX 12, WebGPU, plus Raylib & SDL3 FFI bindings. Pipeline state, shaders, uniform buffers, textures. | Matches Rust wgpu and C++ bgfx cross-platform graphics reach. | 2D/3D Games, CAD, Visual Applications | 9 Days | Critical | Planned
M4-T09 | Month 4 | Sprint 8 (W15-W16) | Game Architecture | Archetype-Based Entity Component System (ECS) | High-performance ECS engine: contiguous component chunk storage (archetypes), query filters (With<T>, Without<U>), and multi-threaded system parallelization. | Matches Rust Bevy ECS and C++ Flecs performance. | Game Engines, Massive Simulations | 7 Days | High | Planned
M4-T10 | Month 4 | Sprint 8 (W15-W16) | Game Audio & Physics | 3D Spatial Audio & Rigid Body Physics Engine | Audio mixer with 3D spatial listener; decoders for WAV, OGG, MP3. Real-time 2D/3D physics: AABB/OBB, GJK/EPA narrowphase, impulse solver, and Raycast. | Complete indie game runtime stack in pure Roze. | Game Development, Interactive Media | 7 Days | High | Planned
M4-T11 | Month 4 | Sprint 8 (W15-W16) | Milestone Gate M4 | Month 4 AI & Game Platform Verification | Run LLaMA 3 token generation streaming demo with zero external C++ code. Launch 60 FPS 3D game demo with ECS, lighting, shadows, physics, and audio. | Stable 60 FPS rendering and validated local LLM generation. | AI/ML & Game Development | 3 Days | Critical | Milestone Gate
M5-T01 | Month 5 | Sprint 9 (W17-W18) | Desktop Windowing | Cross-Platform Native Windowing Engine | Event loop, multi-window creation, DPI scaling, mouse/keyboard/gamepad events, clipboard, and drag-and-drop on Windows (Win32), macOS (Cocoa), Linux (Wayland/X11). | Parity with Rust winit and Java AWT/Swing windowing abstractions. | Desktop Applications, Productivity Software | 7 Days | High | Planned
M5-T02 | Month 5 | Sprint 9 (W17-W18) | Vector 2D Canvas | GPU-Accelerated 2D Vector Rendering Canvas | Path rasterization, cubic bezier curves, SVG path parser, gradient fills, clipping masks, and subpixel anti-aliased font rendering via FreeType/HarfBuzz. | Matches Skia and Rust vello 2D graphics performance. | Desktop GUI, Data Visualization, Creative Tools | 8 Days | High | Planned
M5-T03 | Month 5 | Sprint 9 (W17-W18) | Reactive UI Framework | Declarative Reactive UI ('RozeUI') | Reactive component tree, State<T>, Computed<T>, Effect, two-way data binding, and integrated Flexbox layout engine (Yoga-compatible). | Modern reactive UI matching Flutter, React, and Swift UI. | Desktop Business Apps, Developer Tools | 8 Days | Critical | Planned
M5-T04 | Month 5 | Sprint 9 (W17-W18) | Native Widget Kit | Batteries-Included Desktop Widget Library | Comprehensive widgets: Button, TextInput, TextArea, CheckBox, Dropdown, Slider, DataGrid/Table, TabView, TreeView, SplitPane, Modal Dialogs, Menus. | Matches JavaFX and Qt Widget richness. | Enterprise Desktop Applications | 7 Days | High | Planned
M5-T05 | Month 5 | Sprint 9 (W17-W18) | Desktop Webview | Embedded Webview Component (RozeWebview) | Native embedded browser container: WebView2 on Windows, WKWebView on macOS, WebKitGTK on Linux. Bidirectional JS-Roze bridge communication. | Matches Tauri and Electron capabilities with 1/10th the memory footprint. | Hybrid Desktop Apps, Admin Dashboards | 6 Days | Medium | Planned
M5-T06 | Month 5 | Sprint 10 (W19-W20) | Text & Regex | High-Performance Linear-Time Regex Engine | DFA/NFA regular expression engine with linear O(N) guarantees (no ReDoS catastrophic backtracking), Unicode character classes, capture groups, and lookaheads. | Parity with Rust regex crate and Java java.util.regex. | Text Processing, Compilers, Data Extraction | 7 Days | High | Planned
M5-T07 | Month 5 | Sprint 10 (W19-W20) | Date & Time | Comprehensive Date, Time & Timezone Suite | Instant, Duration, DateTime, TimeZone, ZonedDateTime, IANA timezone database, calendar math (leap seconds, daylight savings), and ISO-8601 parsing. | Complete parity with Java 25 java.time (JSR-310) and Rust chrono. | Enterprise Banking, Scheduling, Databases | 6 Days | High | Planned
M5-T08 | Month 5 | Sprint 10 (W19-W20) | Universal Serialization | Zero-Copy Multi-Format Serialization | High-throughput encoders and decoders for JSON, TOML, YAML, MsgPack, and Protocol Buffers with zero heap allocation deserialization. | Parity with Rust serde and Java Jackson / Google Protobuf. | Microservices, Configs, Game Saves | 7 Days | Critical | Planned
M5-T09 | Month 5 | Sprint 10 (W19-W20) | OS & System Utils | Filesystem, Pipes, Signals & Process Engine | Cross-platform file walking, symbolic links, file watching, inter-process pipes, POSIX/Windows signals, environment variables, and async process spawning. | Matches Rust std::process / std::fs and Java java.nio.file. | DevOps Tooling, CLI Utilities, Systems | 6 Days | High | Planned
M5-T10 | Month 5 | Sprint 10 (W19-W20) | Runtime Metadata | Reflection & Runtime Type Information (RTTI) | Type inspection metadata: struct field enumeration, method discovery, annotation/attribute extraction, and dynamic invoke. | Matches Java reflection and C# metadata reflection. | Frameworks, Serialization, Testing Tools | 6 Days | Medium | Planned
M5-T11 | Month 5 | Sprint 10 (W19-W20) | Milestone Gate M5 | Month 5 Desktop GUI & StdLib Integration | Build and launch cross-platform Desktop Dashboard app in RozeUI displaying real-time system stats, data grids, and embedded webview. | Fluid 60 FPS desktop UI with sub-50ms cold startup time. | Desktop GUI & Standard Utilities | 3 Days | Critical | Milestone Gate
M6-T01 | Month 6 | Sprint 11 (W21-W22) | Pure Roze Frontend | Roze-in-Roze Lexer, Parser & Macro Engine | Rewrite entire compiler frontend in 100% pure Roze: token scanner, recursive descent parser, AST structures, and procedural macro expander supporting all language features. | Zero Rust dependency for Roze compiler syntax analysis. | Self-Hosting Compiler, Language Independence | 8 Days | Critical | Planned
M6-T02 | Month 6 | Sprint 11 (W21-W22) | Pure Roze Semantic | Roze-in-Roze Type Checker & Monomorphizer | Rewrite semantic analyzer in pure Roze: scoped symbol tables, type inference, trait resolution, generic monomorphization, and ARC borrow lifetime analyzer. | Zero Rust dependency for type validation and generic code specialization. | Self-Hosting Compiler, Language Independence | 9 Days | Critical | Planned
M6-T03 | Month 6 | Sprint 11 (W21-W22) | Pure Roze Optimizer | Typed SSA IR & Optimization Passes in Roze | Typed SSA Intermediate Representation with Control Flow Graph (CFG) in pure Roze: Dead Code Elimination, Inlining, Loop Invariant Hoisting, and Constant Folding. | Production compiler optimization engine written in pure Roze. | Self-Hosting Compiler, Performance | 9 Days | Critical | Planned
M6-T04 | Month 6 | Sprint 11 (W21-W22) | Pure Roze Native Backend | Standalone Binary Code Generator in Roze | Direct machine code emitter in pure Roze: output ELF (Linux), Mach-O (macOS), and PE/COFF (Windows) object files, or direct Cranelift/LLVM C-API bindings. | Complete decoupling from Rust toolchain; native standalone binaries built by Roze alone. | Self-Hosting Compiler, Standalone Binaries | 10 Days | Critical | Planned
M6-T05 | Month 6 | Sprint 11 (W21-W22) | Rust Decommissioning | Complete Decommissioning of Rust Host Compiler | Decommission Cargo and rustc from Roze repository build pipeline. The Roze binary itself becomes the primary compiler and build driver. | Ultimate language independence achieved: Roze requires only Roze to build Roze. | Self-Hosting, Autonomy | 5 Days | Critical | Planned
M6-T06 | Month 6 | Sprint 12 (W23-W26) | Bootstrap Fixpoint | 3-Stage Bootstrap Fixpoint Idempotence Verification | Execute automated bootstrap cycle: Stage 0 (Legacy) -> Stage 1 (Roze) -> Stage 2 (Roze) -> Stage 3 (Roze). Run byte-level diff: 'diff bin/roze_stage2 bin/roze_stage3' == 0. | Mathematically verified bootstrap closure (zero byte difference). | Self-Hosting Compiler | 6 Days | Critical | Planned
M6-T07 | Month 6 | Sprint 12 (W23-W26) | Unified Toolchain | Monolithic 'roze' CLI Toolchain Suite | Unify compiler, roze-build, roze-test, roze-fmt, roze-doc, and roze-repl into a single hyper-fast monolithic executable (roze). | Matches the convenience of 'cargo' and 'go' single-binary toolchain. | Developer Experience, Tooling | 6 Days | High | Planned
M6-T08 | Month 6 | Sprint 12 (W23-W26) | Package Registry | Production 'roze-pkg' & Cloud Registry Hub | Deploy production package manager and registry: cryptographic package signing (Ed25519), SAT-based semver dependency solver, lockfiles, and registry server. | Parity with crates.io and npm with built-in security auditing. | Ecosystem Growth, Community | 7 Days | High | Planned
M6-T09 | Month 6 | Sprint 12 (W23-W26) | IDE Ecosystem | Production LSP Server & VS Code Marketplace | Language Server Protocol engine in pure Roze: semantic highlighting, smart completion, go-to-definition, type hover, rename, and formatting in VS Code and JetBrains. | World-class developer tooling experience. | IDE, Developer Productivity | 6 Days | High | Planned
M6-T10 | Month 6 | Sprint 12 (W23-W26) | Final Release M6 | Official Roze v2.0 'Prometheus' Production Launch | Official launch: Finalized grammar specification, 1,000-page standard library documentation, installer packages (deb, rpm, Homebrew, MSI), and RozeHub portal. | Roze v2.0 officially released as an autonomous, general-purpose programming language on par with Java 25 & Rust 1.99.1. | Global Release & Production Ecosystem | 5 Days | Critical | Milestone Gate

## 2. StdLib Architecture
Module Name | Namespace / Import | Core Classes & Structs | Primary Built-in Methods & Functions | Java 25 Benchmark Equivalent | Rust 1.99.1 Benchmark Equivalent | Target Application Scope
Core & Math | roze::core | Int, Float, Bool, String, Char, Math | abs, min, max, clamp, sqrt, sin, cos, tan, pow, log, floor, ceil, round, string_concat, substring, to_upper, to_lower, trim, split, replace, parse_int, parse_float, hash | java.lang.Math, java.lang.String | std::primitive, std::cmp | Universal Fundamentals
Collections | roze::collections | List<T>, Map<K,V>, Set<T>, VecDeque<T>, BTreeMap<K,V>, BinaryHeap<T>, RingBuffer<T>, BitSet | push, pop, get, set, insert, remove, clear, contains, sort, filter, map, reduce, reverse, dedup, binary_search, peek, drain, extend, iter, capacity, shrink_to_fit | java.util (ArrayList, HashMap, TreeSet, PriorityQueue) | std::collections (Vec, HashMap, BTreeMap, BinaryHeap) | Data Structures & Algorithms
Concurrency & Sync | roze::sync | GreenThread, Channel<T>, Mutex<T>, RwLock<T>, AtomicBool, AtomicI64, AtomicPtr, Nursery, Semaphore, Barrier | spawn, sleep, yield_now, channel_new, send, recv, try_recv, lock, read, write, atomic_load, atomic_store, atomic_swap, atomic_add, nursery_open, cancel | java.lang.Thread (Virtual), java.util.concurrent | std::sync, std::thread, crossbeam | Multi-Threading & Parallelism
Async Runtime | roze::async | Future<T>, Task<T>, Poll<T>, Executor, Stream<T>, Sink<T>, Timeout, JoinSet<T> | poll, await, block_on, spawn_async, select, join_all, race, timeout_after, next, send_async, close, is_ready, wake | CompletableFuture, Virtual Threads, Flow API | std::future, tokio runtime | Asynchronous Non-blocking I/O
I/O & Filesystem | roze::io | File, Path, Directory, BufReader, BufWriter, Pipe, Process, Stdin, Stdout, Stderr | read_to_string, read_bytes, write_all, append, delete, exists, create_dir_all, read_dir, canonicalize, copy, rename, spawn_process, pipe_create | java.nio.file (Files, Path), java.io | std::fs, std::io, std::path | Filesystem & OS Interop
Networking & Sockets | roze::net | TcpListener, TcpStream, UdpSocket, DnsResolver, SocketAddr, IpAddr, Ipv4, Ipv6 | bind, accept, connect, read_exact, write_all, send_to, recv_from, set_nodelay, set_read_timeout, resolve_hostname, local_addr, peer_addr | java.net (Socket, ServerSocket, InetAddress) | std::net (TcpStream, UdpSocket) | Low-Level Network I/O
Enterprise Web (RozeBoot) | roze::boot / roze::web | Server, Request, Response, Router, IoCContainer, FilterChain, Middleware, JwtService | start, listen, get, post, put, delete, patch, use_middleware, json_respond, set_header, cookie, redirect, autowire, register_singleton, validate | Spring Boot 3 (Spring MVC, WebFlux) | Actix-web, Axum, Tower | Cloud Microservices & APIs
Database & ORM | roze::orm / roze::sql | ConnectionPool, Connection, QueryBuilder, ResultSet, Entity, Migration, Transaction | pool_create, get_connection, query, execute, begin_transaction, commit, rollback, select, where, join, insert_into, update, migrate_apply | Spring Data JPA, Hibernate, HikariCP | Diesel, SeaORM, sqlx | Enterprise Persistence
Cybersecurity & Raw Net | roze::sec / roze::net::raw | RawSocket, PacketBuilder, Dissector, SynScanner, PcapWriter, MemoryScanner, ShellcodeRunner | raw_socket_open, promiscuous_mode, craft_packet, parse_ethernet, parse_ip, parse_tcp, calculate_checksum, syn_scan, pcap_dump, read_proc_mem, run_shellcode | Jpcap, Pcap4J (Third party) | libpcap bindings, pnet, scapy | Penetration Testing & Hacking
Standard Cryptography | roze::crypto | Aes256Gcm, ChaCha20Poly1305, Sha256, Sha512, Keccak256, HmacSha256, Ed25519, X25519, Rsa4096, TlsSession | encrypt, decrypt, digest, hmac, sign, verify, keygen, diffie_hellman, tls_connect, tls_accept, tls_handshake, random_bytes | java.security, javax.crypto | ring, rustls, ed25519-dalek | Data Protection & Auth
AI & Tensor Engine | roze::ai / roze::tensor | Tensor<T, D>, AutogradTape, Dense, Conv2D, MultiHeadAttention, Transformer, GgufModel, OnnxModel | tensor_new, matmul, add, mul, relu, softmax, layer_norm, backward, forward, load_gguf, load_onnx, tokenize, kv_cache_update, sample_token | Deep Net Java, ND4J, ONNX Runtime Java | burn, candle, tch-rs | Local AI Inference & Training
Game Engine & Graphics | roze::game / roze::gfx | Vec2, Vec3, Vec4, Mat4, Quat, ECS, Window, Texture, Shader, Sound, RigidBody | init_window, clear, draw_sprite, draw_mesh, play_sound, ecs_spawn, ecs_query, physics_step, raycast, apply_force, is_key_down, get_mouse_pos | jMonkeyEngine, libGDX | Bevy, wgpu, raylib-rs | 2D/3D Games & Simulations
OS & Freestanding | roze::os | PageTable, FrameAllocator, GDT, IDT, InterruptHandler, Uart16550, VgaText, GOPFramebuffer, Asm | map_page, unmap_page, alloc_frame, idt_load, gdt_load, outb, inb, uart_write, vga_write_char, asm_execute, disable_interrupts, enable_interrupts | N/A (Java cannot run freestanding) | core::arch, x86_64, bootloader | Operating Systems & Kernels
Desktop GUI (RozeUI) | roze::ui | App, Window, State<T>, Canvas, Button, TextField, DataGrid, Dropdown, Flexbox, Webview | run_app, create_window, set_state, draw_path, draw_text, on_click, on_change, layout_calculate, embed_webview, show_dialog | JavaFX, Swing | Iced, Slint, egui, Tauri | Desktop Applications
Text & Regex | roze::regex | Regex, Match, CaptureGroup, StringBuilder, Formatter, UnicodeScanner | compile, is_match, find, find_all, captures, replace, replace_all, split, append_str, format, graphemes | java.util.regex.Pattern, StringBuilder | regex, unicode-segmentation | Text Manipulation & Compilers
Time & Serialization | roze::time / roze::serialize | Instant, Duration, DateTime, ZonedDateTime, Json, Yaml, Toml, MsgPack, Protobuf | now, elapsed, duration_since, parse_iso8601, format_date, json_serialize, json_deserialize, toml_parse, yaml_parse, protobuf_encode, protobuf_decode | java.time (JSR-310), Jackson, SnakeYAML | chrono, serde_json, toml, rmp | Universal Data Interchange

## 3. 7-Domain Matrix
Target Domain | Vision & Production Capability | Current Roze Baseline | Gaps to Java 25 / Rust 1.99.1 Parity | 6-Month Deliverables & Unlocking Tasks | Industry Benchmark | Target Readiness
Enterprise Web & Microservices | Build enterprise-scale cloud microservices, REST/gRPC backends, connection pooling, and banking-grade APIs with sub-millisecond latency. | Basic JVM/Native HTTP server with JSON and basic JDBC query support. | M:N Virtual Threads, HTTP/2/3 QUIC, Declarative IoC (@Autowired/@Service), High-Throughput ORM, JWT/OAuth2 security filters. | M1-T04, M1-T05, M3-T07, M3-T08, M3-T09, M3-T10 (Sprint 2, 6) | Java 25 (Spring Boot 3), Rust (Actix-web), Go (Gin) | 100% - Spring Boot Parity
Operating Systems & Kernels | Write full 64-bit kernels, bootloaders, microkernels, memory managers, and embedded firmware running directly on bare-metal hardware. | Basic freestanding prototype with simple VGA string printing. | 4-level paging manager, physical frame allocator, full GDT/IDT exception stubs, APIC interrupt controller, inline assembly constraints, UEFI/GOP framebuffer. | M2-T01, M2-T05, M2-T06, M2-T07, M2-T08, M2-T09 (Sprint 3, 4) | C23, Rust 1.99 (#![no_std]), Zig | 100% - Production Kernel Ready
Cybersecurity & Hacking | High-performance security tools: raw network packet sniffers, SYN scanners, protocol dissectors, binary reverse-engineering, and exploit research harnesses. | TCP sockets and basic unsafe pointer allocations. | Promiscuous raw sockets (AF_PACKET/BPF), packet crafting engine (Ethernet->TCP), 100k port/s async scanner, binary disassembler (ELF/PE), process memory inspection. | M2-T01, M3-T01, M3-T02, M3-T03, M3-T04, M3-T05, M3-T06 (Sprint 5) | Python (Scapy), Go, C/C++, Rust | 100% - Security Tooling Suite Ready
AI / Machine Learning | Local LLM inference (LLaMA 3, Mistral), multidimensional tensor math, reverse-mode autograd, and GPU compute without heavy Python runtimes. | Basic 1D/2D float tensors with C wrapper bindings. | N-dimensional Tensor<T, D> with striding/slicing, AVX-512/CUDA GEMM kernels, dynamic Autograd tape, GGUF/ONNX native parser, KV-cache transformer decoder. | M2-T02, M4-T01, M4-T02, M4-T03, M4-T04, M4-T05, M4-T06 (Sprint 7) | Python (PyTorch), C++ (llama.cpp), Mojo, Rust (candle) | 100% - Native AI & LLM Engine Ready
Game Development | 60+ FPS 2D & 3D real-time games, cross-platform graphics, spatial audio, rigid-body physics, and high-performance ECS architectures. | Basic Raylib FFI wrapper demonstrating 2D shape drawing. | Cross-platform graphics HAL (Vulkan, Metal, DirectX 12), archetype-based ECS scheduler, SIMD 3D math suite (Quat, Mat4), 3D spatial audio, rigid-body physics engine. | M1-T03, M2-T02, M4-T07, M4-T08, M4-T09, M4-T10 (Sprint 8) | C++ (Unreal/Raylib), C# (Unity), Rust (Bevy) | 100% - 2D/3D Game Platform Ready
Desktop GUI Applications | Fast, beautiful cross-platform desktop productivity applications with native look-and-feel, GPU 2D vector rendering, and modern reactive state. | Basic window creation without event loop or widget abstractions. | Native windowing & event loop (Win32/Cocoa/Wayland), Skia-style GPU 2D canvas, reactive UI component tree with Flexbox layout, full widget set, embedded Webview. | M5-T01, M5-T02, M5-T03, M5-T04, M5-T05 (Sprint 9) | Java 25 (JavaFX), C# (WPF/.NET MAUI), Rust (Tauri/Slint), C++ (Qt) | 100% - Native Desktop GUI Ready
Embedded & Systems Hardware | Deterministic real-time microcontrollers, IoT devices, automotive systems, and custom hardware peripheral control. | Basic FFI calling convention. | Zero-overhead freestanding target, memory-mapped I/O register abstractions, interrupt service routines, UART/I2C/SPI drivers, bit-manipulation primitives. | M2-T01, M2-T05, M2-T07, M2-T08, M2-T09 (Sprint 3, 4) | C, Rust (embedded-hal), Zig | 100% - Bare-Metal Embedded Ready

## 4. Self-Hosting Roadmap
Stage | Phase Title | Target Component | Technical Deliverable in Pure Roze | Rust Decommissioning Progress | Verification Test & Gate | Status
Stage 0 | Bootstrap Baseline | Rust Host Compiler | Legacy Rust-based Roze compiler (roze-compiler v1.0.0) acts as bootstrap host compiler to compile the initial pure Roze codebase. | 0% - Rust is the build driver | Compile basic Roze programs with Rust host | Completed
Stage 1 | Pure Roze Frontend | Roze-in-Roze Scanner & Parser | Implement complete Token Scanner, Recursive Descent Parser, and Macro Expander in pure Roze (demos/self_hosted/src/frontend/). Supports 100% of Roze grammar. | 25% - Frontend decoupled from Rust | Parse full 10,000 LOC Roze codebase without syntax errors | Planned
Stage 2 | Pure Roze Semantic | Roze-in-Roze Type Checker | Implement Type Checker, Trait Solver, Monomorphizer, and ARC Borrow Checker in pure Roze. Validates symbols, resolves interfaces, and handles generics. | 50% - Semantic analysis decoupled | Type check compiler source with zero errors | Planned
Stage 3 | Pure Roze Optimizer | Roze-in-Roze SSA IR & Optimizer | Implement Typed SSA IR generator and optimization pipeline in pure Roze: Dead Code Elimination, Inlining, Loop Unrolling, Constant Folding, and CFG analysis. | 75% - IR & optimization decoupled | Verify optimized IR passes on benchmark suite | Planned
Stage 4 | Pure Roze Native Backend | Machine Code Emitter & Cranelift | Direct native code generation in pure Roze: emit standalone ELF/Mach-O/PE binaries with Cranelift C-API or standalone assembly generator. Eliminates Cargo. | 90% - Code generation decoupled | Produce standalone native binary from Roze code | Planned
Stage 5 | Fixpoint Closure Verification | 3-Stage Bootstrap Fixpoint | Execute full bootstrap cycle: Stage 0 (Rust) builds roze_stage1; roze_stage1 builds roze_stage2; roze_stage2 builds roze_stage3. Run 'diff roze_stage2 roze_stage3'. | 100% - Zero Rust Dependency! Rust removed. | Fixpoint Verification: diff output is exactly 0 bytes | Milestone Gate

## 5. Sprint Schedule & Gates
Sprint # | Weeks | Milestone Target | Key Technical Epics | Target Deliverables & Acceptance Criteria | Risk Assessment & Mitigation | Quality Gate Sign-Off
Sprint 1 | W01 - W02 | Core Type Power | Generics, Trait Bounds, Pattern Matching, Comptime | Monomorphized generics with bounds, deep pattern matching with guards, comptime expressions. All compiler tests pass. | Risk: Monomorphization code bloat. Mitigation: Deduplicate identical binary representations. | Gate 1: Types Pass
Sprint 2 | W03 - W04 | Concurrency Milestone M1 | M:N Green Threads, Async/Await, Channels, Nurseries | 100,000 green thread stress test, MPMC ring buffer channels, nursery task cancelation. Zero data races. | Risk: Thread starvation. Mitigation: Work-stealing randomized deque scheduler. | Gate 2: Concurrency Sign-Off
Sprint 3 | W05 - W06 | Systems Core & SIMD | Numeric Primitives (i8-u128), SIMD (AVX/NEON), Collections | 15 primitive numeric types, hardware SIMD 8x acceleration, BTreeMap, BinaryHeap, RingBuffer. 100% unit tests. | Risk: Non-aligned SIMD crashes. Mitigation: Enforce 32/64-byte alignment on vector structs. | Gate 3: Systems Core Pass
Sprint 4 | W07 - W08 | Bare-Metal OS Milestone M2 | Freestanding Target, 4-Level Paging, GDT/IDT, Drivers | RozeOS v2 booting in QEMU: paging initialized, IDT exceptions handled, VGA text & GOP graphics running with shell. | Risk: Triple fault on boot. Mitigation: Strict multiboot2 memory map validation. | Gate 4: Kernel Boot Sign-Off
Sprint 5 | W09 - W10 | Security Suite & Crypto | Raw Sockets, Packet Crafting, SYN Scanner, Crypto, Disassembler | Promiscuous packet capture, 100k port/s stealth SYN scanner, pure TLS 1.3 handshake, x86_64 disassembler. | Risk: OS raw socket permissions. Mitigation: Automatic capability checking with fallback. | Gate 5: Security Suite Pass
Sprint 6 | W11 - W12 | Enterprise Web Milestone M3 | RozeBoot 2.0, HTTP/2/3, IoC Container, ORM, JWT, OpenAPI | RozeBoot microservice benchmark: 100k req/s at <1ms latency, auto-generated Swagger UI, SQL connection pool. | Risk: Memory leaks under load. Mitigation: ARC stress testing with leak sanitizers. | Gate 6: RozeBoot Web Sign-Off
Sprint 7 | W13 - W14 | AI & LLM Inference | N-D Tensors, GEMM (AVX/CUDA), Autograd, GGUF/ONNX, LLaMA 3 | Native LLaMA 3 inference generating 45+ tok/s locally; dynamic Autograd training linear regression demo. | Risk: Quantization accuracy loss. Mitigation: Rigorous perplexity testing vs FP16 baseline. | Gate 7: AI Engine Pass
Sprint 8 | W15 - W16 | Game Platform Milestone M4 | 3D Math, Graphics HAL (Vulkan/Metal), Archetype ECS, Audio/Physics | 60 FPS 3D game demo with physics, lighting, shadows, spatial audio, and archetype ECS scheduler running smoothly. | Risk: Frame drops / GC pauses. Mitigation: ARC memory pre-allocation in frame arenas. | Gate 8: Game Platform Sign-Off
Sprint 9 | W17 - W18 | Desktop GUI (RozeUI) | Cross-Platform Windowing, GPU 2D Canvas, Reactive UI, Widgets | Cross-platform Desktop Dashboard app with reactive state, data grid, charts, and embedded Webview container. | Risk: Platform UI quirks. Mitigation: Native platform windowing wrappers for Win32/Cocoa/Wayland. | Gate 9: Desktop GUI Pass
Sprint 10 | W19 - W20 | StdLib Richness Milestone M5 | Linear-Time Regex, Date/Time (JSR-310), Universal Serialization | Zero-ReDoS regex engine, IANA timezone database math, zero-copy JSON/TOML/MsgPack/Protobuf benchmarks. | Risk: Timezone corner cases. Mitigation: Full validation against standard Olson timezone test vectors. | Gate 10: StdLib Parity Sign-Off
Sprint 11 | W21 - W22 | Pure Roze Compiler v2 | Roze-in-Roze Frontend, Type Checker, SSA Optimizer, Native Backend | Compiler rewritten 100% in pure Roze; compiles entire standard library and itself without Rust compiler. | Risk: Compiler bootstrap bug. Mitigation: Extensive golden test fixtures comparing against Stage 0. | Gate 11: Self-Host Frontend Pass
Sprint 12 | W23 - W26 | Production Launch Milestone M6 | Fixpoint Closure (0 Diff), Monolithic CLI, Registry, VS Code, Docs | 3-Stage bootstrap fixpoint verified (0 bytes diff). Official Roze v2.0 'Prometheus' public production release. | Risk: Packaging regressions. Mitigation: Multi-platform automated CI packaging pipeline. | Gate 12: Production Launch Sign-Off